**!. El Paso Children’s Hospital 8th Floor Tenant Improvements**

Description: Build-Out of approximately 26,000 SF of shell space to include 25 new patient bedrooms and associated support and control spaces.

Status: Construction is approximately 40% complete as of this date with Substantial Completion scheduled for October 2024.

Reference: Drawings and Specifications prepared by HKS Inc. dated XXX

**II. El Paso Children’s Hospital Pharmacy Renovation**

Description: Renovation of the existing Pharmacy to comply with USP700 & USP797

Status: Construction is scheduled to commence in the near future date with Substantial Completion scheduled for October 2024.

Reference: Drawings and Specifications prepared by Carl Daniel Architects dated April 3, 2023.

**III. El Paso Children’s Hospital Emergency Expansion**

Description: Renovation and expansion of the interior

Status: Project is currently in the Preliminary Design Phase with Construction Bid documents to be issued in November 2024.

Reference: Preliminary Design drawings prepared by HKS Inc. dated April XXX

**IV. UMC Sterile Processing Renovation**

Description: Renovation of the existing Sterile Processing Department to replace four washers, four sterilizers and a new cart wash

Status: Construction is scheduled to commence on May 7, 2024 with Substantial Completion by October 14, 2024

Reference: Drawings and Specifications prepared by FOKUS Architects dated March 21, 2024.

**V. UMC Thomason Tower 8th Floor Renovation**

Description: Renovation of the 8th floor of Thomason Tower to include 25 new Patient Observation rooms in addition to support and public areas.

Status: Project is currently in the Preliminary Design Phase with Construction Bid documents to be issued in November 2024.

Reference: Project Narrative 50% Preliminary Design dated February 15, 2024